## Instructions
Using the Status tracker
At the end of each week, update the status of all activities completed during the week
The status tracker shown in this worksheet is an example tracker (values filled are during the middle of the week)
Fill in hours spent on each activity during the current week
If 5 team members each spent an hour, that counts as 5 hours
Fill in time for activities not fully completed ("ongoing") as well, then update these values during following weeks
During the planning phases, identify the activities to be done during each week
If you spend time on an activity not listed in the tracker, add the activity and list actual hours (need not fill in estimated hours if you didn't estimate it up front)
For new activities, identify the type of activity - documentation, coordination, estimation etc.
At the end of each week, plan ahead for the following week
Identify people responsible for each activity
Estimate the hours needed for the activity
TEAM NAME | Team Lamp
PROJECT NAME | Stampitgo : BEACON
PROJECT MENTOR | Amar Budhiraja
TEAM MEMBERS | Aaditya M Nair
Parth Kolekar
Vamsee Reddy
Tinku Monish

## Team_Status
TEAM NAME | 22
PROJECT NAME | Extract Transform Load
PROJECT MENTOR | Juhi Tandon
Activity Name | Type | Responsible | Estimated Team Hours | Actual Hours | Status | Comments | Estimation error | Estimation error %
See Instructions sheet for usage
Week 6 (sept 5- sept 11)
Learn Backbone.js | Preparation | All | 4 | 7 | Ongoing | Learn how to implement it | -3 | 42.8571
Learn Java Server Pages | Preparation | All | 5 | 8 | Ongoing | Using for backend | -3 | 37.5
Front End Backbone.js part | Development | Abdulla and Avinash | 8 | 10 | Planned | Implementing home page | -2 | 20
Front End Html and Css | Development | Ravi Teja and M Sowmith | 4 | 5 | Planned | Implementing home page | -1 | 20
Getting used with kettle | Preparation | All | 5 | 5 | Planned | Getting used to it | 0 | 0
Week 7 (sept 12 - sept 18)
Started with AngularJS | Development | Avinash | 4 | 6 | Ongoing | Learn how to implement it | -2 | 33.3333
Home Page (Back-end) | Development | Ravi Teja | 2 | 4 | Ongoing | Working with MVC | -2 | 50
Home Page (Front-end) | Design | M Sowmith | 3 | 6 | Done | Design Work | -3 | 50
Week 8 (sept 19 - sept 25)
Week 9
Week 10
Week 11
Week 12
Week 13
Week 14
Week 15
Week 16
Week 17

## Individual_Status
TEAM NAME | Team LAMP
PROJECT NAME | Stampitgo: BEACON
PROJECT MENTOR | Amar Budhiraja
Actvities | Aaditya M Nair |  | Parth Kolekar |  | Vamsee Reddy |  | Tinku Monish |  | Estimated Total Hours | Actual Total Hours
| Estimated Time | Actual Time Spent | Estimated Time | Actual Time Spent | Estimated Time | Actual Time Spent | Estimated Time | Actual Time Spent
Week 6 (sept 5- sept 11)
Learn Backbone.js | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 8 | 0
Learn Java Server Pages | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 8 | 0
Front End Backbone.js part | 3 | 0 | 4 | 0 | 2 | 0 | 2 | 0 | 11 | 0
Front End Html and Css | 4 | 0 | 3 | 0 | 2 | 0 | 2 | 0 | 11 | 0
Getting used with kettle | 0.5 | 0 | 0.5 | 0 | 0.5 | 0 | 0.5 | 0 | 2 | 0
Getting used with kettle | 4 | 0 | 4 | 0 | 4 | 0 | 4 | 0 | 16 | 0
Make Ping Test With AWS Server | 5 | 0 | 5 | 0 | 5 | 0 | 5 | 0 | 20 | 0
Week 7 (sept 12 - sept 18)
Started with AngularJS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Home Page (Back-end) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Home Page (Front-end) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Week 8 (sept 19 - sept 25)
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Week 9
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Week 10
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Week 11
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Week 12
0 | [8 empty] | 0 | 0
0 | [8 empty] | 0 | 0
0
0
Week 13
0 | [8 empty] | 0 | 0
0
0
0
Week 14
0 | [8 empty] | 0 | 0
0
0
0
Week 15
0 | [8 empty] | 0 | 0
0
0
Week 16
0 | [8 empty] | 0 | 0
0
0
0
Week 17
0 | [8 empty] | 0 | 0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0